## Slide 1
BSUC 510A:Stop subscriber provisioning when license capacity reached
Summary/Overall progress/Risks: BSUC: c510a (Status) - There is not much change because final merge, dod ( on hold till finally delivery) and rest is mentioned below. CPI review is on final-stage. NFNT of BSUC_c510a is not required anymore(Received approval from the SAT). Functional Testing is started & will completed by coming Monday. |  |  | 
Decisions/Actions needed: |  |  | 
Overall Progress: BSUC-study in sharp version: Yes ID approved by SAT: No ID planned. Documentation on track: Yes NFNT on track: On-Going and on-track Summary:98% | Cost: Actual hours estimated for BSUC: 647 hrs Design/FT revised estimation after last sprint: 11 hrs remaining |  | Important dates Start: 2017-10-20 Scheduled delivery date to support team: Not decided Planned target drop (BSUCs, NIPs): 1816 Planned release: 18A? (PCP/ICP/R&D Release)
Status
Planned delivery to master
Status
current sprint
Notes: Patrik Oscarsson
2017-06-30
© Ericsson AB 2014
1
EAB/KDB/OR/Benny Rasmussen
2014-09-17
© Ericsson AB 2014
1
NOTE: if information is unclear regarding expected delivery dates, please check with PMs and/or ReleaseTeCs (depending on question)
Important dates:
Keep those that are applicable for either BSUC or PC – the rest you can erase or put N/A on…

## Slide 2
BSUC 287b_1: To control charging of data traffic service based on the configuration set by subscriber handset
Summary/Overall progress/Risks: BSUC: c287b_1(Status) - Development is started. Java code is committed and reviews are on-going. Cipip Test is committed and Reviews are on going. TTCN framework(epkshared) changes are in review. New TTCN test cases are in progress. |  |  | 
Decisions/Actions needed: |  |  | 
Overall Progress: BSUC-study in sharp version: Yes ID approved by SAT: No ID planned. Documentation on track: Yes NFNT on track: On-Going and on-track Summary:59 % | Cost: Actual hours estimated for BSUC: 344 hrs Design/FT revised estimation after last sprint: 142 hrs remaining |  | Important dates Start: 2018-01-22 Scheduled delivery date to support team: Not decided Planned target drop (BSUCs, NIPs): 1816 Planned release: 18A? (PCP/ICP/R&D Release)
Status
Planned delivery to master
Status
current sprint
Notes: Patrik Oscarsson
2017-06-30
© Ericsson AB 2014
2
EAB/KDB/OR/Benny Rasmussen
2014-09-17
© Ericsson AB 2014
2
NOTE: if information is unclear regarding expected delivery dates, please check with PMs and/or ReleaseTeCs (depending on question)
Important dates:
Keep those that are applicable for either BSUC or PC – the rest you can erase or put N/A on…

## Slide 3
Other assigned work
Summary/Overall progress/Risks: Other Assigned Work - Praveen: Involved in the TTCN review of the BSUC :287A_B Involved in the Code & review of the BSUC:287A_B , which is on-going Adarsh : • Involved in the tree testing of the BSUC:287A_B Abhishek : Analysis of Snart Test case failure . Rakesh : Regression Test analysis for DTS Time zone done. Learning: Abhishek , Adarsh , Rakesh : • Simulating test case of Cipiptest and analyzing.
Notes: Patrik Oscarsson
2017-06-30
© Ericsson AB 2014
3
EAB/KDB/OR/Benny Rasmussen
2014-09-17
© Ericsson AB 2014
3
NOTE: if information is unclear regarding expected delivery dates, please check with PMs and/or ReleaseTeCs (depending on question)
Important dates:
Keep those that are applicable for either BSUC or PC – the rest you can erase or put N/A on…